## Meridian - S2P Project
Project Name | Project Category | Ancestors | Project Manager | Level | Phase/Milestone | At Risk? | Schedule Health | Task Name | Status | Start Date | End Date | % Complete | On Hold? | Not Applicable? | Duration | Predecessors | Description | Owner | OwnerShip | Priority | Total Float | Critical ? | Baseline Start | Baseline Finish | Variance | Status Comment | Area | Comments | Assigned To | Start | Finish | RAG
| S2P Implementation | 0 | Kavita Deshmukh | 0 |  |  | Yellow | Zycus - Meridian S2P Implementation | In Progress | 2026-01-12 | 2026-11-20 | 0.52 |  |  | 312 | [5 empty] | 0 | TRUE | 2026-01-12 | 2026-11-20 | 0d |  |  |  |  | 2026-01-12 | 2026-11-20 | Yellow
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Green | Design - Task 1 | Not Started | 2026-05-06 | 2026-05-13 | 0 |  |  | 7 |  |  | Neha Kulkarni |  |  | -1 | [8 empty] | 2026-05-06 | 2026-05-13
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | Build - Task 2 | Completed | 2026-04-01 | 2026-04-10 | 1 |  |  | 9 |  |  | Sameer Iyer |  |  | 12 | [8 empty] | 2026-04-01 | 2026-04-10 | Red
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Green | Discovery - Task 3 | Completed | 2026-02-21 | 2026-03-03 | 1 |  |  | 10 | [5 empty] | 20 | [8 empty] | 2026-02-21 | 2026-03-03 | Yellow
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Configuration - Task 4 | Completed | 2026-02-09 | 2026-02-19 | 1 |  |  | 10 |  |  | Divya Shah |  |  | 12 | [8 empty] | 2026-02-09 | 2026-02-19 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Yellow | Go-Live - Task 5 | In Progress | 2026-03-23 | 2026-04-11 | 0.9 |  |  | 19 | [5 empty] | 2 |  | 2026-03-26 | 2026-04-13 | 2d |  |  |  | Priya Menon | 2026-03-23 | 2026-04-11 | Green
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Yellow | Go-Live - Task 6 | Not Started | 2026-05-26 | 2026-06-14 | 0 |  |  | 19 |  |  | Priya Menon |  |  | 60 | [8 empty] | 2026-05-26 | 2026-06-14 | Green
| S2P Implementation | 3 | Kavita Deshmukh | 3 | Testing |  | Green | Testing - Task 7 | Not Started | 2026-02-21 | 2026-02-26 | 0 |  |  | 5 |  |  | Priya Menon |  |  | 0 | [8 empty] | 2026-02-21 | 2026-02-26
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Hypercare - Task 8 | Not Started | 2026-07-04 | 2026-07-07 | 0 |  |  | 3 | [5 empty] | 5 | [8 empty] | 2026-07-04 | 2026-07-07
| S2P Implementation | 2 | Kavita Deshmukh | 1 | Hypercare |  | Green | Hypercare - Task 9 | Completed | 2026-03-02 | 2026-03-26 | 1 |  |  | 24 |  |  | Neha Kulkarni |  |  | 35 |  | 2026-02-27 | 2026-03-23 | -3d |  |  |  |  | 2026-03-02 | 2026-03-26 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | Design - Task 10 | Not Started | 2026-01-19 | 2026-01-24 | 0 |  |  | 5 | [5 empty] | 5 | [8 empty] | 2026-01-19 | 2026-01-24
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Green | Build - Task 11 | Not Started | 2026-02-10 | 2026-03-03 | 0 |  |  | 21 | [5 empty] | 0 | [8 empty] | 2026-02-10 | 2026-03-03 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 2 | Discovery |  | Green | Discovery - Task 12 | Completed | 2026-10-06 | 2026-10-19 | 1 |  |  | 13 |  |  | Neha Kulkarni |  |  | 5 |  |  |  |  | Awaiting vendor sign-off, expected next week |  |  |  | 2026-10-06 | 2026-10-19 | Yellow
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | UAT - Task 13 | Not Started | 2026-10-17 | 2026-11-11 | 0 |  |  | 25 |  |  | Arjun Rao |  |  | -1 |  | 2026-10-12 | 2026-11-14 | 3d |  |  |  | Client IT | 2026-10-17 | 2026-11-11 | Red
| S2P Implementation | 2 | Kavita Deshmukh | 1 | Discovery |  | Green | Discovery - Task 14 | Not Started | 2026-06-02 | 2026-06-06 | 0 |  |  | 4 |  |  | Neha Kulkarni |  |  | 8 |  | 2026-06-03 | 2026-05-30 | -7d | On track, no issues |  |  |  | 2026-06-02 | 2026-06-06 | Yellow
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Green | Configuration - Task 15 | Completed | 2026-07-12 | 2026-08-01 | 1 |  |  | 20 | [5 empty] | 20 | [7 empty] | Client IT | 2026-07-12 | 2026-08-01
| S2P Implementation | 2 | Kavita Deshmukh | 1 | Design |  | Yellow | Design - Task 16 | In Progress | 2026-09-09 | 2026-09-19 | 0.13 |  |  | 10 | [5 empty] | 8 |  | 2026-09-05 | 2026-09-17 | -2d |  |  |  | Priya Menon | 2026-09-09 | 2026-09-19
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Yellow | Discovery - Task 17 | Not Started | 2026-06-21 | 2026-07-07 | 0 |  |  | 16 | [5 empty] | 60 | [8 empty] | 2026-06-21 | 2026-07-07
| S2P Implementation | 2 | Kavita Deshmukh | 2 | UAT |  | Green | UAT - Task 18 | Completed | 2026-06-14 | 2026-07-03 | 1 |  |  | 19 | [5 empty] | 20 |  | 2026-06-11 | 2026-07-01 | -2d |  |  |  |  | 2026-06-14 | 2026-07-03
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | UAT - Task 19 | In Progress | 2026-05-01 | 2026-05-20 | 0.45 |  |  | 19 | [5 empty] | 0 |  | 2026-05-02 | 2026-05-13 | -7d |  |  |  |  | 2026-05-01 | 2026-05-20
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Red | Go-Live - Task 20 | In Progress | 2026-01-14 | 2026-01-20 | 0.3 |  |  | 6 | [5 empty] | 5 | [8 empty] | 2026-01-14 | 2026-01-20
| S2P Implementation | 2 | Kavita Deshmukh | 3 | Go-Live |  | Green | Go-Live - Task 21 | Completed | 2026-04-03 | 2026-04-21 | 1 |  |  | 18 |  |  | Arjun Rao |  |  | 8 |  | 2026-04-03 | 2026-04-14 | -7d |  |  |  |  | 2026-04-03 | 2026-04-21 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | Hypercare - Task 22 | In Progress | 2026-08-15 | 2026-08-30 | 0.27 |  |  | 15 | [5 empty] | -3 | [8 empty] | 2026-08-15 | 2026-08-30
| S2P Implementation | 1 | Kavita Deshmukh | 1 | Hypercare |  | Red | Hypercare - Task 23 | Not Started | 2026-01-26 | 2026-02-10 | 0 |  |  | 15 |  |  | Arjun Rao |  |  | 2 |  | 2026-01-23 | 2026-02-02 | -8d |  |  |  | Client IT | 2026-01-26 | 2026-02-10
| S2P Implementation | 3 | Kavita Deshmukh | 1 | Go-Live |  | Green | Go-Live - Task 24 | Not Started | 2026-08-15 | 2026-08-26 | 0 |  |  | 11 | [5 empty] | 35 | TRUE | [6 empty] | Sameer Iyer | 2026-08-15 | 2026-08-26 | Green
| S2P Implementation | 3 | Kavita Deshmukh | 3 | Hypercare |  | Green | Hypercare - Task 25 | Completed | 2026-04-07 | 2026-04-29 | 1 |  |  | 22 | [5 empty] | 0 | [7 empty] | Vendor Team | 2026-04-07 | 2026-04-29
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Green | Design - Task 26 | Completed | 2026-02-02 | 2026-02-16 | 1 |  |  | 14 | [5 empty] | 60 |  | 2026-01-31 | 2026-02-18 | 2d |  |  |  |  | 2026-02-02 | 2026-02-16
| S2P Implementation | 2 | Kavita Deshmukh | 2 |  |  | Green | Hypercare - Task 27 | In Progress | 2026-05-29 | 2026-06-11 | 0.68 |  |  | 13 | [5 empty] | 0 | [7 empty] | Neha Kulkarni | 2026-05-29 | 2026-06-11 | Red
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | Configuration - Task 28 | Not Started | 2026-09-19 | 2026-10-09 | 0 |  |  | 20 | [5 empty] | 35 | [7 empty] | Priya Menon | 2026-09-19 | 2026-10-09
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Configuration - Task 29 | Not Started | 2026-03-14 | 2026-04-03 | 0 |  |  | 20 |  |  | Neha Kulkarni |  |  | 2 | [8 empty] | 2026-03-14 | 2026-04-03 | Red
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Build - Task 30 | Completed | 2026-03-05 | 2026-03-08 | 1 |  |  | 3 |  |  | Sameer Iyer |  |  | 35 | [7 empty] | Client IT | 2026-03-05 | 2026-03-08 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 1 | Go-Live |  | Green | Go-Live - Task 31 | Completed | 2026-05-07 | 2026-05-26 | 1 |  |  | 19 | [5 empty] | -3 |  | 2026-05-03 | 2026-05-25 | -1d |  |  |  |  | 2026-05-07 | 2026-05-26 | Yellow
| S2P Implementation | 1 | Kavita Deshmukh | 1 | Hypercare |  | Red | Hypercare - Task 32 | Not Started | 2026-06-05 | 2026-06-30 | 0 |  |  | 25 | [5 empty] | 0 | [8 empty] | 2026-06-05 | 2026-06-30
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Green | Testing - Task 33 | In Progress | 2026-06-16 | 2026-07-11 | 0.47 |  |  | 25 | [5 empty] | 60 |  | 2026-06-15 | 2026-07-06 | -5d |  |  |  | Divya Shah | 2026-06-16 | 2026-07-11 | Green
| S2P Implementation | 1 | Kavita Deshmukh | 2 | Hypercare |  | Green | Hypercare - Task 34 | Completed | 2026-08-23 | 2026-09-15 | 1 |  |  | 23 |  |  | Neha Kulkarni |  |  | 0 | [8 empty] | 2026-08-23 | 2026-09-15
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Go-Live - Task 35 | Completed | 2026-01-12 | 2026-02-05 | 1 |  |  | 24 | [5 empty] | 35 | [7 empty] | Sameer Iyer | 2026-01-12 | 2026-02-05
| S2P Implementation | 1 | Kavita Deshmukh | 2 | Testing |  | Green | Testing - Task 36 | In Progress | 2026-02-28 | 2026-03-10 | 0.54 |  |  | 10 | [5 empty] | 0 | [8 empty] | 2026-02-28 | 2026-03-10
| S2P Implementation | 2 | Kavita Deshmukh | 2 |  |  | Green | Build - Task 37 | Completed | 2026-08-12 | 2026-08-25 | 1 |  |  | 13 | [5 empty] | 60 | [8 empty] | 2026-08-12 | 2026-08-25
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Green | Configuration - Task 38 | In Progress | 2026-08-10 | 2026-08-14 | 0.29 |  |  | 4 | [5 empty] | 20 |  | 2026-08-06 | 2026-08-06 | -8d |  |  |  |  | 2026-08-10 | 2026-08-14
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | Go-Live - Task 39 | Completed | 2026-02-19 | 2026-03-09 | 1 |  |  | 18 |  |  | Priya Menon |  |  | 8 | [8 empty] | 2026-02-19 | 2026-03-09
| S2P Implementation | 3 | Kavita Deshmukh | 3 | Design |  | Green | Design - Task 40 | In Progress | 2026-03-04 | 2026-03-21 | 0.18 |  |  | 17 | [5 empty] | 0 |  | 2026-03-03 | 2026-03-24 | 3d |  |  |  | Arjun Rao | 2026-03-04 | 2026-03-21
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Red | Testing - Task 41 | In Progress | 2026-09-07 | 2026-09-19 | 0.63 |  |  | 12 |  |  | Priya Menon |  |  | 2 | [8 empty] | 2026-09-07 | 2026-09-19
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Red | Testing - Task 42 | Not Started | 2026-08-02 | 2026-08-13 | 0 |  |  | 11 | [5 empty] | 35 |  | 2026-08-05 | 2026-08-07 | -6d |  |  |  |  | 2026-08-02 | 2026-08-13
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Green | Testing - Task 43 | Completed | 2026-07-17 | 2026-07-24 | 1 |  |  | 7 | [5 empty] | 20 |  | 2026-07-16 | 2026-07-22 | -2d |  |  |  | Client IT | 2026-07-17 | 2026-07-24 | Red
| S2P Implementation | 2 | Kavita Deshmukh | 3 | Configuration |  | Green | Configuration - Task 44 | Completed | 2026-08-03 | 2026-08-23 | 1 |  |  | 20 |  |  | Arjun Rao |  |  | 8 |  | 2026-07-31 | 2026-08-26 | 3d |  |  |  |  | 2026-08-03 | 2026-08-23
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | Testing - Task 45 | Completed | 2026-02-04 | 2026-02-08 | 1 |  |  | 4 | [5 empty] | 0 |  | 2026-01-31 | 2026-02-10 | 2d |  |  |  |  | 2026-02-04 | 2026-02-08
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | Testing - Task 46 | Not Started | 2026-08-27 | 2026-09-13 | 0 |  |  | 17 |  |  | Priya Menon |  |  | 12 | [7 empty] | Sameer Iyer | 2026-08-27 | 2026-09-13 | Yellow
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Configuration - Task 47 | Not Started | 2026-04-28 | 2026-05-19 | 0 |  |  | 21 |  |  | Neha Kulkarni |  |  | 2 |  | 2026-04-28 | 2026-05-17 | -2d |  |  |  | Arjun Rao | 2026-04-28 | 2026-05-19 | Red
| S2P Implementation | 2 | Kavita Deshmukh | 3 | Design |  | Red | Design - Task 48 | Completed | 2026-07-16 | 2026-08-04 | 1 |  |  | 19 | [5 empty] | 35 | [8 empty] | 2026-07-16 | 2026-08-04
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | Design - Task 49 | Not Started | 2026-03-17 | 2026-03-28 | 0 |  |  | 11 | [5 empty] | -3 | [8 empty] | 2026-03-17 | 2026-03-28
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Green | Hypercare - Task 50 | In Progress | 2026-06-21 | 2026-07-07 | 0.68 |  |  | 16 | [5 empty] | 2 |  | 2026-06-20 | 2026-07-05 | -2d | On track, no issues |  |  |  | 2026-06-21 | 2026-07-07
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | Discovery - Task 51 | Completed | 2026-07-11 | 2026-07-17 | 1 |  |  | 6 |  |  | Priya Menon |  |  | 5 | [7 empty] | Priya Menon | 2026-07-11 | 2026-07-17
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | Testing - Task 52 | Completed | 2026-04-14 | 2026-04-21 | 1 |  |  | 7 |  |  | Divya Shah |  |  | 20 | [7 empty] | Neha Kulkarni | 2026-04-14 | 2026-04-21
| S2P Implementation | 1 | Kavita Deshmukh | 2 | Testing |  | Green | Testing - Task 53 | In Progress | 2026-08-26 | 2026-09-11 | 0.44 |  |  | 16 |  |  | Arjun Rao |  |  | 12 |  | 2026-08-21 | 2026-09-13 | 2d | On track, no issues |  |  |  | 2026-08-26 | 2026-09-11
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Green | Build - Task 54 | Not Started | 2026-05-09 | 2026-05-28 | 0 |  |  | 19 |  |  | Divya Shah |  | High | -1 | [8 empty] | 2026-05-09 | 2026-05-28 | Green
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Yellow | UAT - Task 55 | Not Started | 2026-05-16 | 2026-06-01 | 0 |  |  | 16 | [5 empty] | 60 | [7 empty] | Neha Kulkarni | 2026-05-16 | 2026-06-01
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Green | Build - Task 56 | Not Started | 2026-03-31 | 2026-04-23 | 0 |  |  | 23 | [5 empty] | -3 |  | 2026-03-27 | 2026-04-19 | -4d |  |  |  |  | 2026-03-31 | 2026-04-23
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Red | Design - Task 57 | Not Started | 2026-02-10 | 2026-02-24 | 0 |  |  | 14 | [5 empty] | 0 |  |  |  |  | Resource constraint on client side, monitoring |  |  |  | 2026-02-10 | 2026-02-24
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | UAT - Task 58 | Completed | 2026-04-10 | 2026-04-14 | 1 |  |  | 4 |  |  | Divya Shah |  |  | 60 |  | 2026-04-06 | 2026-04-10 | -4d |  |  |  |  | 2026-04-10 | 2026-04-14 | Green
| S2P Implementation | 3 | Kavita Deshmukh | 3 | UAT |  | Green | UAT - Task 59 | Not Started | 2026-07-10 | 2026-07-22 | 0 |  |  | 12 | [5 empty] | -1 | [8 empty] | 2026-07-10 | 2026-07-22
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Red | Discovery - Task 60 | In Progress | 2026-05-01 | 2026-05-14 | 0.24 |  |  | 13 |  |  | Divya Shah |  |  | 35 | [8 empty] | 2026-05-01 | 2026-05-14
| S2P Implementation | 2 | Kavita Deshmukh | 2 |  |  | Yellow | Build - Task 61 | Completed | 2026-07-17 | 2026-08-10 | 1 |  |  | 24 | [5 empty] | 35 | [8 empty] | 2026-07-17 | 2026-08-10
| S2P Implementation | 2 | Kavita Deshmukh | 2 |  |  | Green | Go-Live - Task 62 | Completed | 2026-03-23 | 2026-04-03 | 1 |  |  | 11 | [5 empty] | 60 |  | 2026-03-19 | 2026-04-01 | -2d |  |  |  |  | 2026-03-23 | 2026-04-03 | Yellow
| S2P Implementation | 1 | Kavita Deshmukh | 2 | UAT |  | Green | UAT - Task 63 | Not Started | 2026-07-22 | 2026-08-01 | 0 |  |  | 10 |  |  | Divya Shah |  |  | -1 |  | 2026-07-24 | 2026-07-24 | -8d |  |  |  |  | 2026-07-22 | 2026-08-01
| S2P Implementation | 3 | Kavita Deshmukh | 3 | Design |  | Green | Design - Task 64 | Completed | 2026-03-15 | 2026-03-19 | 1 |  |  | #UNPARSEABLE | [5 empty] | 0 |  | 2026-03-11 | 2026-03-21 | 2d |  |  |  | Divya Shah | 2026-03-15 | 2026-03-19 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Green | Discovery - Task 65 | In Progress | 2026-07-29 | 2026-08-12 | 0.48 |  |  | 14 | [5 empty] | 0 |  | 2026-08-01 | 2026-08-10 | -2d |  |  |  | Client IT | 2026-07-29 | 2026-08-12
| S2P Implementation | 2 | Kavita Deshmukh | 2 |  |  | Green | Hypercare - Task 66 | Not Started | 2026-04-24 | 2026-04-28 | 0 |  |  | 4 | [5 empty] | 20 |  | 2026-04-23 | 2026-04-23 | -5d |  |  |  |  | 2026-04-24 | 2026-04-28 | Red
| S2P Implementation | 2 | Kavita Deshmukh | 2 | Build |  | Green | Build - Task 67 | In Progress | 2026-10-04 | 2026-10-15 | 0.5 |  |  | 11 | [5 empty] | 20 | [8 empty] | 2026-10-04 | 2026-10-15
| S2P Implementation | 2 | Kavita Deshmukh | 2 |  |  | Yellow | Go-Live - Task 68 | Not Started | 2026-02-10 | 2026-02-15 | 0 |  |  | 5 | [5 empty] | 20 | [8 empty] | 2026-02-10 | 2026-02-15
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Green | Hypercare - Task 69 | Completed | 2026-02-20 | 2026-03-13 | 1 |  |  | 21 | [5 empty] | 12 |  | 2026-02-18 | 2026-03-10 | -3d |  |  |  | Client IT | 2026-02-20 | 2026-03-13
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Design - Task 70 | In Progress | 2026-08-27 | 2026-09-01 | 0.82 |  |  | 5 |  |  | Arjun Rao |  |  | 12 | [7 empty] | Divya Shah | 2026-08-27 | 2026-09-01 | Yellow
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Red | UAT - Task 71 | In Progress | 2026-03-19 | 2026-04-10 | 0.89 |  |  | 22 | [5 empty] | 0 | [8 empty] | 2026-03-19 | 2026-04-10
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Green | Build - Task 72 | Completed | 2026-09-26 | 2026-09-30 | 1 |  |  | 4 | [5 empty] | 60 | [7 empty] | Vendor Team | 2026-09-26 | 2026-09-30
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Red | Build - Task 73 | In Progress | 2026-04-09 | 2026-05-03 | 0.56 |  |  | 24 | [5 empty] | -3 | [7 empty] | Priya Menon | 2026-04-09 | 2026-05-03
| S2P Implementation | 3 | Kavita Deshmukh | 3 | Hypercare |  | Green | Hypercare - Task 74 | Not Started | 2026-08-07 | 2026-08-19 | 0 |  |  | 12 |  |  | Neha Kulkarni |  |  | 35 |  | 2026-08-10 | 2026-08-20 | 1d |  |  |  | Sameer Iyer | 2026-08-07 | 2026-08-19
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Build - Task 75 | Not Started | 2026-07-27 | 2026-08-18 | 0 |  |  | 22 |  |  | Arjun Rao |  |  | -3 |  | 2026-07-28 | 2026-08-16 | -2d |  |  |  |  | 2026-07-27 | 2026-08-18 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 3 | Hypercare |  | Green | Hypercare - Task 76 | Not Started | 2026-03-08 | 2026-03-24 | 0 |  |  | 16 | [5 empty] | 12 |  | 2026-03-07 | 2026-03-16 | -8d |  |  |  |  | 2026-03-08 | 2026-03-24
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Green | UAT - Task 77 | In Progress | 2026-03-26 | 2026-04-04 | 0.39 |  |  | 9 |  |  | Priya Menon |  |  | 20 | [8 empty] | 2026-03-26 | 2026-04-04 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 2 | Hypercare |  | Yellow | Hypercare - Task 78 | Completed | 2026-01-20 | 2026-02-03 | 1 |  |  | 14 | [5 empty] | -3 |  | 2026-01-22 | 2026-01-31 | -3d |  |  |  |  | 2026-01-20 | 2026-02-03 | Green
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | Go-Live - Task 79 | Not Started | 2026-01-28 | 2026-02-18 | 0 |  |  | 21 | [5 empty] | 0 | [8 empty] | 2026-01-28 | 2026-02-18
| S2P Implementation | 2 | Kavita Deshmukh | 3 | Hypercare |  | Green | Hypercare - Task 80 | In Progress | 2026-04-10 | 2026-04-27 | 0.35 |  |  | 17 | [5 empty] | 12 | [7 empty] | Priya Menon | 2026-04-10 | 2026-04-27 | Red
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Red | Testing - Task 81 | Not Started | 2026-10-17 | 2026-11-01 | 0 |  |  | 15 | [5 empty] | 20 | [7 empty] | Divya Shah | 2026-10-17 | 2026-11-01 | Yellow
| S2P Implementation | 2 | Kavita Deshmukh | 2 |  |  | Green | Configuration - Task 82 | Not Started | 2026-10-10 | 2026-10-20 | 0 |  |  | 10 | [5 empty] | 0 | [7 empty] | Priya Menon | 2026-10-10 | 2026-10-20
| S2P Implementation | 2 | Kavita Deshmukh | 1 | Discovery |  | Green | Discovery - Task 83 | Completed | 2026-05-10 | 2026-05-30 | 1 |  |  | 20 | [5 empty] | 0 | [7 empty] | Priya Menon | 2026-05-10 | 2026-05-30
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | Testing - Task 84 | In Progress | 2026-10-07 | 2026-10-25 | 0.61 |  |  | 18 |  |  | Arjun Rao |  |  | 2 | [8 empty] | 2026-10-07 | 2026-10-25
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Green | UAT - Task 85 | Not Started | 2026-04-16 | 2026-04-23 | 0 |  |  | 7 | [5 empty] | 8 |  | 2026-04-16 | 2026-04-26 | 3d |  |  |  |  | 2026-04-16 | 2026-04-23
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Testing - Task 86 | Completed | 2026-06-12 | 2026-06-26 | 1 |  |  | 14 | [5 empty] | 5 | [7 empty] | Arjun Rao | 2026-06-12 | 2026-06-26
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Green | UAT - Task 87 | Not Started | 2026-02-12 | 2026-03-04 | 0 |  |  | 20 | [5 empty] | 5 | [7 empty] | Arjun Rao | 2026-02-12 | 2026-03-04
| S2P Implementation | 2 | Kavita Deshmukh | 2 |  |  | Green | Testing - Task 88 | Completed | 2026-01-13 | 2026-01-22 | 1 |  |  | 9 | [5 empty] | 0 | [8 empty] | 2026-01-13 | 2026-01-22
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Red | Design - Task 89 | Completed | 2026-10-15 | 2026-10-22 | 1 |  |  | 7 |  |  | Arjun Rao |  |  | 12 | [7 empty] | Priya Menon | 2026-10-15 | 2026-10-22
| S2P Implementation | 2 | Kavita Deshmukh | 2 | Configuration |  | Red | Configuration - Task 90 | Completed | 2026-03-10 | 2026-03-14 | 1 |  |  | 4 |  |  | Neha Kulkarni |  |  | 20 | [7 empty] | Priya Menon | 2026-03-10 | 2026-03-14 | Green
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Configuration - Task 91 | Completed | 2026-06-24 | 2026-07-15 | 1 |  |  | 21 | [5 empty] | -1 | [7 empty] | Priya Menon | 2026-06-24 | 2026-07-15
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Yellow | Go-Live - Task 92 | Completed | 2026-08-13 | 2026-08-29 | 1 |  |  | 16 |  |  | Arjun Rao |  |  | 60 |  | 2026-08-10 | 2026-08-30 | 1d |  |  |  |  | 2026-08-13 | 2026-08-29 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Green | Design - Task 93 | In Progress | 2026-02-07 | 2026-02-18 | 0.76 |  |  | 11 | [5 empty] | 5 |  | 2026-02-10 | 2026-02-20 | 2d |  |  |  |  | 2026-02-07 | 2026-02-18 | Green
| S2P Implementation | 3 | Kavita Deshmukh | 1 | Go-Live |  | Yellow | Go-Live - Task 94 | Completed | 2026-06-05 | 2026-06-20 | 1 |  |  | 15 | [5 empty] | 8 |  | 2026-06-03 | 2026-06-19 | -1d |  |  |  |  | 2026-06-05 | 2026-06-20 | Yellow
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Go-Live - Task 95 | Not Started | 2026-05-09 | 2026-05-24 | 0 |  |  | 15 | [5 empty] | 5 | [8 empty] | 2026-05-09 | 2026-05-24
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Discovery - Task 96 | In Progress | 2026-02-19 | 2026-03-15 | 0.77 | Yes |  | 24 | [5 empty] | 2 |  | 2026-02-22 | 2026-03-12 | -3d |  |  |  | Vendor Team | 2026-02-19 | 2026-03-15
| S2P Implementation | 1 | Kavita Deshmukh | 3 | Testing |  | Green | Testing - Task 97 | In Progress | 2026-09-26 | 2026-10-21 | 0.33 |  |  | 25 | [5 empty] | 2 | [8 empty] | 2026-09-26 | 2026-10-21
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Yellow | Discovery - Task 98 | Not Started | 2026-10-21 | 2026-11-08 | 0 |  |  | 18 |  |  | Neha Kulkarni |  |  | 2 |  | 2026-10-24 | 2026-10-31 | -8d |  |  |  |  | 2026-10-21 | 2026-11-08
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | Testing - Task 99 | Completed | 2026-01-28 | 2026-02-05 | 1 |  |  | 8 | [5 empty] | 12 | TRUE | [6 empty] | Vendor Team | 2026-01-28 | 2026-02-05
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Red | Design - Task 100 | In Progress | 2026-02-08 | 2026-02-14 | 0.88 |  |  | 6 |  |  | Divya Shah |  | Medium | -3 |  | 2026-02-10 | 2026-02-12 | -2d |  |  |  | Sameer Iyer | 2026-02-08 | 2026-02-14 | Yellow
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Design - Task 101 | Not Started | 2026-03-31 | 2026-04-15 | 0 |  |  | 15 |  |  | Arjun Rao |  |  | 0 |  | 2026-04-02 | 2026-04-17 | 2d |  |  |  | Arjun Rao | 2026-03-31 | 2026-04-15
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Green | Go-Live - Task 102 | Completed | 2026-05-16 | 2026-06-06 | 1 |  |  | 21 | [5 empty] | 2 |  | 2026-05-13 | 2026-06-07 | 1d |  |  |  | Neha Kulkarni | 2026-05-16 | 2026-06-06
| S2P Implementation | 2 | Kavita Deshmukh | 2 | Go-Live |  | Green | Go-Live - Task 103 | Not Started | 2026-06-29 | 2026-07-16 | 0 |  |  | 17 | [5 empty] | 12 |  | 2026-06-30 | 2026-07-15 | -1d |  |  |  |  | 2026-06-29 | 2026-07-16
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | Configuration - Task 104 | In Progress | 2026-10-20 | 2026-10-23 | 0.54 |  |  | 3 | [5 empty] | 35 | [7 empty] | Divya Shah | 2026-10-20 | 2026-10-23 | Red
| S2P Implementation | 2 | Kavita Deshmukh | 1 | Hypercare |  | Red | Hypercare - Task 105 | In Progress | 2026-08-14 | 2026-09-03 | 0.53 |  |  | 20 |  |  | Divya Shah |  |  | 60 |  | 2026-08-12 | 2026-08-26 | -8d |  |  |  |  | 2026-08-14 | 2026-09-03 | Red
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Red | Configuration - Task 106 | In Progress | 2026-09-25 | 2026-10-02 | 0.41 |  |  | 7 |  |  | Priya Menon |  |  | 0 |  | 2026-09-28 | 2026-09-28 | -4d |  |  |  | Vendor Team | 2026-09-25 | 2026-10-02 | Green
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Green | Design - Task 107 | Not Started | 2026-03-08 | 2026-04-01 | 0 |  |  | 24 |  |  | Sameer Iyer |  |  | 5 | [7 empty] | Client IT | 2026-03-08 | 2026-04-01
| S2P Implementation | 3 | Kavita Deshmukh | 3 | Design |  | Yellow | Design - Task 108 | In Progress | 2026-10-13 | 2026-10-21 | 0.74 |  |  | 8 |  |  | Neha Kulkarni |  |  | 0 |  | 2026-10-13 | 2026-10-17 | -4d |  |  |  | Neha Kulkarni | 2026-10-13 | 2026-10-21 | Red
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | Build - Task 109 | In Progress | 2026-07-29 | 2026-08-14 | 0.21 |  |  | 16 | [5 empty] | -3 | [8 empty] | 2026-07-29 | 2026-08-14
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Green | Configuration - Task 110 | Completed | 2026-09-27 | 2026-10-20 | 1 |  |  | 23 | [5 empty] | 35 |  | 2026-09-23 | 2026-10-17 | -3d |  |  |  | Divya Shah | 2026-09-27 | 2026-10-20
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Green | UAT - Task 111 | In Progress | 2026-08-25 | 2026-09-14 | 0.71 |  |  | 20 | [5 empty] | -1 |  | 2026-08-22 | 2026-09-16 | 2d |  |  |  |  | 2026-08-25 | 2026-09-14
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Red | Build - Task 112 | Completed | 2026-02-11 | 2026-03-04 | 1 |  |  | 21 | [5 empty] | 60 |  | 2026-02-10 | 2026-02-26 | -6d |  |  |  | Client IT | 2026-02-11 | 2026-03-04
| S2P Implementation | 2 | Kavita Deshmukh | 3 | Build |  | Green | Build - Task 113 | Not Started | 2026-05-18 | 2026-06-11 | 0 |  |  | 24 | [5 empty] | -1 |  | 2026-05-19 | 2026-06-05 | -6d |  |  |  |  | 2026-05-18 | 2026-06-11
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Yellow | Hypercare - Task 114 | Completed | 2026-02-13 | 2026-03-05 | 1 |  |  | 20 |  |  | Arjun Rao |  |  | 35 |  | 2026-02-10 | 2026-03-05 | 0d | Awaiting vendor sign-off, expected next week |  |  | Arjun Rao | 2026-02-13 | 2026-03-05
| S2P Implementation | 3 | Kavita Deshmukh | 1 | Configuration |  | Green | Configuration - Task 115 | Completed | 2026-06-15 | 2026-06-23 | 1 |  |  | 8 | [5 empty] | 8 | [7 empty] | Sameer Iyer | 2026-06-15 | 2026-06-23 | Green
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Hypercare - Task 116 | Not Started | 2026-03-14 | 2026-03-30 | 0 |  |  | 16 | [5 empty] | 35 | [7 empty] | Priya Menon | 2026-03-14 | 2026-03-30 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | Configuration - Task 117 | Completed | 2026-08-10 | 2026-09-01 | 1 |  |  | 22 |  |  | Neha Kulkarni |  |  | 5 | [8 empty] | 2026-08-10 | 2026-09-01
| S2P Implementation | 3 | Kavita Deshmukh | 3 | Testing |  | Green | Testing - Task 118 | Not Started | 2026-04-18 | 2026-05-03 | 0 |  |  | 15 | [5 empty] | 35 |  | 2026-04-21 | 2026-05-03 | 0d |  | IT |  |  | 2026-04-18 | 2026-05-03 | Red
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Design - Task 119 | Not Started | 2026-05-26 | 2026-06-04 | 0 |  |  | 9 | [5 empty] | 60 |  | 2026-05-29 | 2026-06-01 | -3d |  |  |  |  | 2026-05-26 | 2026-06-04 | Yellow
| S2P Implementation | 1 | Kavita Deshmukh | 2 | Design |  | Green | Design - Task 120 | Not Started | 2026-05-14 | 2026-05-18 | 0 |  |  | 4 | [5 empty] | 35 |  | 2026-05-11 | 2026-05-20 | 2d |  | Finance |  | Neha Kulkarni | 2026-05-14 | 2026-05-18 | Red
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Discovery - Task 121 | Not Started | 2026-10-07 | 2026-10-12 | 0 |  |  | 5 |  |  | Neha Kulkarni |  |  | 35 |  | 2026-10-09 | 2026-10-08 | -4d |  |  |  |  | 2026-10-07 | 2026-10-12
| S2P Implementation | 1 | Kavita Deshmukh | 2 | Go-Live |  | Green | Go-Live - Task 122 | Completed | 2026-01-30 | 2026-02-19 | 1 |  |  | 20 | [5 empty] | -1 | [7 empty] | Client IT | 2026-01-30 | 2026-02-19
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Testing - Task 123 | Not Started | 2026-01-16 | 2026-01-30 | 0 |  |  | 14 | [5 empty] | -3 |  | 2026-01-15 | 2026-01-22 | -8d |  |  |  |  | 2026-01-16 | 2026-01-30
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | Discovery - Task 124 | Completed | 2026-07-23 | 2026-08-04 | 1 |  |  | 12 | [5 empty] | 20 |  | 2026-07-18 | 2026-08-04 | 0d |  |  |  |  | 2026-07-23 | 2026-08-04 | Green
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Green | Discovery - Task 125 | In Progress | 2026-05-13 | 2026-05-25 | 0.87 |  |  | 12 | [5 empty] | 12 |  | 2026-05-11 | 2026-05-22 | -3d |  |  |  |  | 2026-05-13 | 2026-05-25
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | Design - Task 126 | Not Started | 2026-02-01 | 2026-02-10 | 0 |  |  | 9 |  |  | Neha Kulkarni |  |  | 12 | [8 empty] | 2026-02-01 | 2026-02-10
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Build - Task 127 | Not Started | 2026-05-05 | 2026-05-12 | 0 |  |  | 7 |  |  | Divya Shah |  |  | -1 |  | 2026-05-02 | 2026-05-10 | -2d |  |  |  |  | 2026-05-05 | 2026-05-12 | Red
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Go-Live - Task 128 | In Progress | 2026-08-18 | 2026-08-26 | 0.41 |  |  | 8 | [5 empty] | 8 |  | 2026-08-19 | 2026-08-25 | -1d |  |  |  |  | 2026-08-18 | 2026-08-26
| S2P Implementation | 1 | Kavita Deshmukh | 1 | Discovery |  | Green | Discovery - Task 129 | Completed | 2026-07-14 | 2026-08-01 | 1 |  |  | 18 | [5 empty] | -3 |  | 2026-07-10 | 2026-07-30 | -2d |  |  |  | Client IT | 2026-07-14 | 2026-08-01
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Green | Discovery - Task 130 | Completed | 2026-07-29 | 2026-08-12 | 1 |  |  | 14 | [5 empty] | 2 | [7 empty] | Sameer Iyer | 2026-07-29 | 2026-08-12 | Yellow
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Yellow | Configuration - Task 131 | Not Started | 2026-06-30 | 2026-07-22 | 0 |  |  | 22 |  |  | Neha Kulkarni |  |  | 2 |  | 2026-07-01 | 2026-07-20 | -2d |  |  |  | Priya Menon | 2026-06-30 | 2026-07-22
| S2P Implementation | 2 | Kavita Deshmukh | 1 | Build |  | Green | Build - Task 132 | Completed | 2026-08-23 | 2026-09-15 | 1 |  |  | 23 |  |  | Divya Shah |  |  | -1 | [8 empty] | 2026-08-23 | 2026-09-15
| S2P Implementation | 2 | Kavita Deshmukh | 1 | Discovery |  | Green | Discovery - Task 133 | Not Started | 2026-05-05 | 2026-05-28 | 0 |  |  | 23 |  |  | Neha Kulkarni |  |  | 35 | [8 empty] | 2026-05-05 | 2026-05-28
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Green | Design - Task 134 | Completed | 2026-08-24 | 2026-09-09 | 1 |  |  | 16 | [5 empty] | 20 | [7 empty] | Sameer Iyer | 2026-08-24 | 2026-09-09 | Green
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | Go-Live - Task 135 | Not Started | 2026-02-28 | 2026-03-13 | 0 |  |  | 13 | [5 empty] | -3 | [7 empty] | Neha Kulkarni | 2026-02-28 | 2026-03-13
| S2P Implementation | 2 | Kavita Deshmukh | 2 |  |  | Green | Discovery - Task 136 | In Progress | 2026-09-20 | 2026-09-27 | 0.54 |  |  | 7 |  |  | Divya Shah |  | High | 0 |  | 2026-09-23 | 2026-09-24 | -3d |  |  |  |  | 2026-09-20 | 2026-09-27
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Green | UAT - Task 137 | Completed | 2026-08-28 | 2026-09-01 | 1 |  |  | 4 | [5 empty] | 5 |  | 2026-08-24 | 2026-08-31 | -1d |  |  |  |  | 2026-08-28 | 2026-09-01 | Green
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Yellow | Hypercare - Task 138 | In Progress | 2026-06-14 | 2026-06-19 | 0.29 |  |  | 5 | [5 empty] | -3 |  | 2026-06-17 | 2026-06-14 | -5d |  |  |  |  | 2026-06-14 | 2026-06-19
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Build - Task 139 | Completed | 2026-02-15 | 2026-02-20 | 1 |  |  | 5 |  |  | Priya Menon |  |  | 12 |  | 2026-02-12 | 2026-02-15 | -5d |  |  |  |  | 2026-02-15 | 2026-02-20
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Green | UAT - Task 140 | Completed | 2026-09-17 | 2026-10-08 | 1 |  |  | 21 | [5 empty] | 0 |  |  |  |  | Delayed due to scope clarification with stakeholders |  |  | Client IT | 2026-09-17 | 2026-10-08
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Green | Hypercare - Task 141 | Completed | 2026-05-08 | 2026-05-15 | 1 |  |  | 7 | [5 empty] | 8 |  | 2026-05-04 | 2026-05-13 | -2d |  |  |  |  | 2026-05-08 | 2026-05-15 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | Discovery - Task 142 | Not Started | 2026-04-24 | 2026-04-28 | 0 |  |  | 4 |  |  | Priya Menon |  |  | 12 |  | 2026-04-20 | 2026-05-01 | 3d |  |  |  |  | 2026-04-24 | 2026-04-28
| S2P Implementation | 1 | Kavita Deshmukh | 1 | Design |  | Green | Design - Task 143 | Not Started | 2026-04-05 | 2026-04-26 | 0 |  |  | 21 | [5 empty] | 5 |  |  |  |  | Resource constraint on client side, monitoring |  |  | Vendor Team | 2026-04-05 | 2026-04-26
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Green | Testing - Task 144 | In Progress | 2026-07-09 | 2026-07-26 | 0.4 | Yes |  | 17 |  |  | Priya Menon |  |  | -1 |  | 2026-07-05 | 2026-07-25 | -1d |  |  |  |  | 2026-07-09 | 2026-07-26 | Green
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Green | Testing - Task 145 | Completed | 2026-06-13 | 2026-06-22 | 1 |  |  | 9 |  |  | Divya Shah |  |  | -3 |  | 2026-06-13 | 2026-06-25 | 3d |  |  |  |  | 2026-06-13 | 2026-06-22
| S2P Implementation | 1 | Kavita Deshmukh | 2 | Hypercare |  | Green | Hypercare - Task 146 | Completed | 2026-09-28 | 2026-10-10 | 1 |  |  | 12 | [5 empty] | -1 | [8 empty] | 2026-09-28 | 2026-10-10 | Green
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Yellow | UAT - Task 147 | In Progress | 2026-09-06 | 2026-09-12 | 0.57 |  |  | 6 |  |  | Neha Kulkarni |  |  | 5 |  | 2026-09-08 | 2026-09-08 | -4d |  |  |  |  | 2026-09-06 | 2026-09-12
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Yellow | Build - Task 148 | Not Started | 2026-08-31 | 2026-09-11 | 0 |  |  | 11 | [5 empty] | 2 |  | 2026-09-01 | 2026-09-05 | -6d | Resource constraint on client side, monitoring |  |  | Neha Kulkarni | 2026-08-31 | 2026-09-11
| S2P Implementation | 2 | Kavita Deshmukh | 1 | Configuration |  | Yellow | Configuration - Task 149 | Not Started | 2026-06-20 | 2026-06-27 | 0 |  |  | 7 | [5 empty] | 8 |  | 2026-06-15 | 2026-06-21 | -6d |  |  |  |  | 2026-06-20 | 2026-06-27
| S2P Implementation | 3 | Kavita Deshmukh | 1 | Discovery |  | Green | Discovery - Task 150 | Not Started | 2026-03-20 | 2026-03-29 | 0 |  |  | 9 |  |  | Arjun Rao |  |  | -3 | [8 empty] | 2026-03-20 | 2026-03-29 | Green
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Green | Testing - Task 151 | In Progress | 2026-01-16 | 2026-01-28 | 0.22 |  |  | 12 |  |  | Arjun Rao |  |  | 60 |  | 2026-01-18 | 2026-01-21 | -7d |  |  |  | Neha Kulkarni | 2026-01-16 | 2026-01-28 | Yellow
| S2P Implementation | 2 | Kavita Deshmukh | 2 | Hypercare |  | Yellow | Hypercare - Task 152 | Completed | 2026-09-15 | 2026-09-28 | 1 |  |  | 13 | [5 empty] | 0 |  | 2026-09-18 | 2026-09-21 | -7d |  |  |  |  | 2026-09-15 | 2026-09-28 | Red
| S2P Implementation | 2 | Kavita Deshmukh | 2 |  |  | Green | Testing - Task 153 | In Progress | 2026-08-18 | 2026-08-24 | 0.64 |  |  | 6 | [5 empty] | 2 |  | 2026-08-21 | 2026-08-27 | 3d |  |  |  |  | 2026-08-18 | 2026-08-24
| S2P Implementation | 2 | Kavita Deshmukh | 1 | Build |  | Green | Build - Task 154 | Not Started | 2026-02-11 | 2026-02-19 | 0 |  |  | 8 | [5 empty] | -1 |  | 2026-02-07 | 2026-02-13 | -6d |  |  |  | Client IT | 2026-02-11 | 2026-02-19
| S2P Implementation | 2 | Kavita Deshmukh | 1 | Configuration |  | Green | Configuration - Task 155 | Completed | 2026-07-04 | 2026-07-23 | 1 |  |  | 19 | [5 empty] | -1 |  | 2026-07-06 | 2026-07-20 | -3d | Resource constraint on client side, monitoring |  |  | Priya Menon | 2026-07-04 | 2026-07-23
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Yellow | Discovery - Task 156 | In Progress | 2026-07-24 | 2026-08-08 | 0.54 |  |  | 15 | [5 empty] | 0 | [8 empty] | 2026-07-24 | 2026-08-08
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Yellow | Testing - Task 157 | Completed | 2026-09-02 | 2026-09-15 | 1 |  |  | 13 | [5 empty] | 35 |  | 2026-09-05 | 2026-09-15 | 0d | On track, no issues |  |  | Sameer Iyer | 2026-09-02 | 2026-09-15
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Green | Hypercare - Task 158 | Not Started | 2026-08-09 | 2026-08-15 | 0 |  |  | 6 | [5 empty] | 0 |  | 2026-08-09 | 2026-08-15 | 0d |  |  |  |  | 2026-08-09 | 2026-08-15
| S2P Implementation | 2 | Kavita Deshmukh | 2 |  |  | Yellow | Discovery - Task 159 | In Progress | 2026-08-21 | 2026-09-11 | 0.14 |  |  | 21 | [5 empty] | -3 |  | 2026-08-16 | 2026-09-12 | 1d |  |  |  |  | 2026-08-21 | 2026-09-11 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | Build - Task 160 | Not Started | 2026-10-01 | 2026-10-13 | 0 |  |  | 12 | [5 empty] | 60 | [7 empty] | Neha Kulkarni | 2026-10-01 | 2026-10-13
| S2P Implementation | 3 | Kavita Deshmukh | 2 | UAT |  | Yellow | UAT - Task 161 | In Progress | 2026-08-13 | 2026-09-06 | 0.57 |  |  | 24 |  |  | Priya Menon |  | High | 60 | [7 empty] | Divya Shah | 2026-08-13 | 2026-09-06
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Yellow | Discovery - Task 162 | In Progress | 2026-05-06 | 2026-05-29 | 0.46 |  |  | 23 |  |  | Arjun Rao |  |  | 5 | [8 empty] | 2026-05-06 | 2026-05-29
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | UAT - Task 163 | Completed | 2026-04-22 | 2026-05-01 | 1 |  |  | 9 | [5 empty] | 0 |  | 2026-04-23 | 2026-04-24 | -7d |  |  |  |  | 2026-04-22 | 2026-05-01 | Yellow
| S2P Implementation | 2 | Kavita Deshmukh | 2 | Testing |  | Red | Testing - Task 164 | In Progress | 2026-07-14 | 2026-07-19 | 0.56 |  |  | 5 | [5 empty] | 12 | [8 empty] | 2026-07-14 | 2026-07-19 | Red
| S2P Implementation | 2 | Kavita Deshmukh | 2 | Discovery |  | Green | Discovery - Task 165 | Not Started | 2026-05-15 | 2026-06-07 | 0 |  |  | 23 | [5 empty] | -3 |  |  |  |  | On track, no issues |  |  | Divya Shah | 2026-05-15 | 2026-06-07
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Design - Task 166 | Completed | 2026-10-14 | 2026-11-03 | 1 |  |  | 20 |  |  | Priya Menon |  |  | -1 |  | 2026-10-16 | 2026-11-03 | 0d |  |  |  | Neha Kulkarni | 2026-10-14 | 2026-11-03
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Discovery - Task 167 | Not Started | 2026-02-17 | 2026-03-10 | #UNPARSEABLE |  |  | 21 |  |  | Divya Shah |  |  | 8 | [7 empty] | Client IT | 2026-02-17 | 2026-03-10
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | Testing - Task 168 | Completed | 2026-08-24 | 2026-09-08 | 1 |  |  | 15 | [5 empty] | 2 |  | 2026-08-27 | 2026-09-04 | -4d |  |  |  |  | 2026-08-24 | 2026-09-08
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Red | Build - Task 169 | Not Started | 2026-08-01 | 2026-08-21 | 0 |  |  | 20 | [5 empty] | 5 |  | 2026-08-03 | 2026-08-20 | -1d |  |  |  |  | 2026-08-01 | 2026-08-21 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Green | Hypercare - Task 170 | Completed | 2026-02-15 | 2026-02-26 | 1 |  |  | 11 | [5 empty] | 12 |  | 2026-02-11 | 2026-02-24 | -2d |  |  |  | Priya Menon | 2026-02-15 | 2026-02-26
| S2P Implementation | 3 | Kavita Deshmukh | 1 | Configuration |  | Green | Configuration - Task 171 | Completed | 2026-08-23 | 2026-09-03 | 1 |  |  | 11 | [5 empty] | 2 | [7 empty] | Neha Kulkarni | 2026-08-23 | 2026-09-03 | Yellow
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Red | Discovery - Task 172 | Completed | 2026-08-07 | 2026-08-28 | 1 |  |  | 21 |  |  | Sameer Iyer |  |  | 8 |  | 2026-08-10 | 2026-08-23 | -5d |  |  |  |  | 2026-08-07 | 2026-08-28
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Red | Build - Task 173 | Completed | 2026-04-03 | 2026-04-11 | 1 |  |  | 8 | [5 empty] | -3 | [8 empty] | 2026-04-03 | 2026-04-11 | Yellow
| S2P Implementation | 2 | Kavita Deshmukh | 2 |  |  | Green | Discovery - Task 174 | Completed | 2026-10-05 | 2026-10-28 | 1 |  |  | 23 | [5 empty] | 8 | [8 empty] | 2026-10-05 | 2026-10-28
| S2P Implementation | 1 | Kavita Deshmukh | 1 | Build |  | Green | Build - Task 175 | In Progress | 2026-10-02 | 2026-10-25 | 0.28 |  |  | 23 | [5 empty] | 2 |  | 2026-10-03 | 2026-10-26 | 1d |  |  |  | Vendor Team | 2026-10-02 | 2026-10-25
| S2P Implementation | 2 | Kavita Deshmukh | 1 | Discovery |  | Green | Discovery - Task 176 | Completed | 2026-04-07 | 2026-04-18 | 1 |  |  | 11 | [5 empty] | 60 | [7 empty] | Divya Shah | 2026-04-07 | 2026-04-18
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | Build - Task 177 | Completed | 2026-04-07 | 2026-05-01 | 1 |  |  | 24 | [5 empty] | -3 |  | 2026-04-03 | 2026-04-25 | -6d |  |  |  |  | 2026-04-07 | 2026-05-01
| S2P Implementation | 1 | Kavita Deshmukh | 2 | Design |  | Green | Design - Task 178 | In Progress | 2026-10-15 | 2026-10-18 | 0.2 |  |  | 3 | [5 empty] | -1 | [7 empty] | Client IT | 2026-10-15 | 2026-10-18
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Green | Design - Task 179 | Not Started | 2026-08-09 | 2026-08-20 | 0 |  |  | 11 |  |  | Arjun Rao |  |  | 60 |  | 2026-08-12 | 2026-08-14 | -6d |  |  |  |  | 2026-08-09 | 2026-08-20
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Go-Live - Task 180 | In Progress | 2026-04-13 | 2026-04-27 | 0.55 |  |  | 14 | [5 empty] | 35 | [8 empty] | 2026-04-13 | 2026-04-27 | Yellow
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Discovery - Task 181 | Not Started | 2026-01-14 | 2026-01-19 | 0 |  |  | 5 | [5 empty] | 35 | [7 empty] | Vendor Team | 2026-01-14 | 2026-01-19
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Testing - Task 182 | Not Started | 2026-09-30 | 2026-10-19 | 0 | Yes |  | 19 | [5 empty] | -3 | [8 empty] | 2026-09-30 | 2026-10-19
| S2P Implementation | 3 | Kavita Deshmukh | 3 | UAT |  | Green | UAT - Task 183 | Not Started | 2026-05-07 | 2026-05-29 | 0 |  |  | 22 | [5 empty] | 35 | [8 empty] | 2026-05-07 | 2026-05-29
| S2P Implementation | 2 | Kavita Deshmukh | 1 | Hypercare |  | Green | Hypercare - Task 184 | Completed | 2026-09-03 | 2026-09-27 | 1 |  |  | 24 |  |  | Priya Menon |  |  | 0 |  | 2026-09-06 | 2026-09-23 | -4d |  |  |  | Sameer Iyer | 2026-09-03 | 2026-09-27
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Hypercare - Task 185 | Not Started | 2026-05-29 | 2026-06-06 | 0 |  |  | 8 | [5 empty] | -1 | [8 empty] | 2026-05-29 | 2026-06-06 | Green
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Discovery - Task 186 | Completed | 2026-06-22 | 2026-07-10 | 1 |  |  | 18 | [5 empty] | -3 | [8 empty] | 2026-06-22 | 2026-07-10
| S2P Implementation | 2 | Kavita Deshmukh | 2 | Hypercare |  | Green | Hypercare - Task 187 | Completed | 2026-09-04 | 2026-09-17 | 1 |  |  | 13 | [5 empty] | 0 | [8 empty] | 2026-09-04 | 2026-09-17 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Yellow | Go-Live - Task 188 | Not Started | 2026-03-20 | 2026-04-10 | 0 |  |  | 21 | [5 empty] | 0 |  |  |  |  | Delayed due to scope clarification with stakeholders |  |  | Client IT | 2026-03-20 | 2026-04-10
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Discovery - Task 189 | In Progress | 2026-02-11 | 2026-02-20 | 0.65 |  |  | 9 | [5 empty] | 35 | [7 empty] | Client IT | 2026-02-11 | 2026-02-20
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Testing - Task 190 | In Progress | 2026-09-18 | 2026-10-05 | 0.64 |  |  | 17 |  |  | Priya Menon |  |  | 20 | [8 empty] | 2026-09-18 | 2026-10-05
| S2P Implementation | 3 | Kavita Deshmukh | 1 | Go-Live |  | Green | Go-Live - Task 191 | Not Started | 2026-07-16 | 2026-08-06 | 0 |  |  | 21 |  |  | Neha Kulkarni |  |  | 2 |  | 2026-07-12 | 2026-08-03 | -3d |  |  |  | Divya Shah | 2026-07-16 | 2026-08-06
| S2P Implementation | 3 | Kavita Deshmukh | 2 | Build |  | Green | Build - Task 192 | Not Started | 2026-07-30 | 2026-08-11 | 0 |  |  | 12 | [5 empty] | -1 |  | 2026-07-29 | 2026-08-07 | -4d |  |  |  |  | 2026-07-30 | 2026-08-11
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | Hypercare - Task 193 | Completed | 2026-08-22 | 2026-09-10 | 1 |  |  | 19 | [5 empty] | 60 |  |  |  |  | Resource constraint on client side, monitoring |  |  |  | 2026-08-22 | 2026-09-10
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Yellow | Testing - Task 194 | Not Started | 2026-06-10 | 2026-07-02 | 0 |  |  | 22 |  |  | Divya Shah |  |  | 12 |  | 2026-06-13 | 2026-06-27 | -5d |  |  |  |  | 2026-06-10 | 2026-07-02
| S2P Implementation | 3 | Kavita Deshmukh | 1 | Go-Live |  | Green | Go-Live - Task 195 | Not Started | 2026-03-22 | 2026-04-03 | 0 |  |  | 12 |  |  | Arjun Rao |  |  | 35 |  | 2026-03-18 | 2026-03-28 | -6d |  |  |  | Arjun Rao | 2026-03-22 | 2026-04-03
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Yellow | Testing - Task 196 | Completed | 2026-07-21 | 2026-08-07 | 1 |  |  | 17 | [5 empty] | 0 | [8 empty] | 2026-07-21 | 2026-08-07
| S2P Implementation | 2 | Kavita Deshmukh | 3 | Hypercare |  | Red | Hypercare - Task 197 | Not Started | 2026-04-23 | 2026-05-10 | 0 |  |  | 17 |  |  | Neha Kulkarni |  |  | 0 | [8 empty] | 2026-04-23 | 2026-05-10 | Red
| S2P Implementation | 2 | Kavita Deshmukh | 3 | Configuration |  | Green | Configuration - Task 198 | Completed | 2026-08-22 | 2026-09-04 | 1 |  |  | 13 |  |  | Sameer Iyer |  |  | 0 |  | 2026-08-21 | 2026-08-29 | -6d |  |  |  |  | 2026-08-22 | 2026-09-04
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Green | Design - Task 199 | Not Started | 2026-07-08 | 2026-07-25 | 0 |  |  | 17 | [5 empty] | 0 | [8 empty] | 2026-07-08 | 2026-07-25 | Red
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Build - Task 200 | Not Started | 2026-06-12 | 2026-06-23 | 0 |  |  | 11 | [5 empty] | -1 |  | 2026-06-08 | 2026-06-26 | 3d |  |  |  | Priya Menon | 2026-06-12 | 2026-06-23
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Green | UAT - Task 201 | In Progress | 2026-03-02 | 2026-03-21 | 0.36 |  |  | 19 | [5 empty] | 0 | [7 empty] | Sameer Iyer | 2026-03-02 | 2026-03-21
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Yellow | Hypercare - Task 202 | Completed | 2026-09-08 | 2026-10-01 | 1 |  |  | 23 |  |  | Divya Shah |  |  | 20 |  | 2026-09-03 | 2026-09-23 | -8d |  |  |  |  | 2026-09-08 | 2026-10-01 | Green
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Green | Build - Task 203 | In Progress | 2026-03-07 | 2026-03-30 | 0.55 |  |  | 23 |  |  | Priya Menon |  |  | -1 | [8 empty] | 2026-03-07 | 2026-03-30 | Red
| S2P Implementation | 1 | Kavita Deshmukh | 2 | Go-Live |  | Green | Go-Live - Task 204 | Completed | 2026-05-15 | 2026-06-05 | #UNPARSEABLE | Yes |  | 21 | [5 empty] | 8 |  | 2026-05-12 | 2026-05-31 | -5d |  |  |  |  | 2026-05-15 | 2026-06-05 | Yellow
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Yellow | Testing - Task 205 | Completed | 2026-04-01 | 2026-04-07 | 1 |  |  | 6 | [5 empty] | 2 |  | 2026-03-30 | 2026-04-08 | 1d |  |  |  |  | 2026-04-01 | 2026-04-07
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Yellow | Design - Task 206 | In Progress | 2026-07-26 | 2026-07-31 | 0.34 |  |  | 5 |  |  | Divya Shah |  |  | 12 |  |  |  |  | Delayed due to scope clarification with stakeholders |  |  |  | 2026-07-26 | 2026-07-31
| S2P Implementation | 2 | Kavita Deshmukh | 3 | Build |  | Green | Build - Task 207 | Not Started | 2026-08-01 | 2026-08-18 | 0 |  |  | 17 |  |  | Divya Shah |  |  | -3 | [7 empty] | Arjun Rao | 2026-08-01 | 2026-08-18
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Green | Configuration - Task 208 | In Progress | 2026-10-07 | 2026-10-17 | 0.9 |  |  | 10 | [5 empty] | 12 |  | 2026-10-06 | 2026-10-14 | -3d |  |  |  |  | 2026-10-07 | 2026-10-17 | Red
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Red | Configuration - Task 209 | Not Started | 2026-02-24 | 2026-03-02 | 0 |  |  | 6 |  |  |  |  | Low | 5 | [8 empty] | 2026-02-24 | 2026-03-02
| S2P Implementation | 1 | Kavita Deshmukh | 1 | Build |  | Green | Build - Task 210 | Completed | 2026-07-23 | 2026-08-13 | 1 |  |  | #UNPARSEABLE | [5 empty] | 60 | TRUE | [7 empty] | 2026-07-23 | 2026-08-13 | Red
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Green | Go-Live - Task 211 | In Progress | 2026-06-22 | 2026-07-10 | 0.67 |  |  | 18 |  |  | Priya Menon |  |  | 60 | [7 empty] | Divya Shah | 2026-06-22 | 2026-07-10
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Green | Testing - Task 212 | Completed | 2026-07-29 | 2026-08-01 | 1 |  |  | 3 | [5 empty] | 8 | [7 empty] | Divya Shah | 2026-07-29 | 2026-08-01
| S2P Implementation | 3 | Kavita Deshmukh | 3 | Build |  | Green | Build - Task 213 | Not Started | 2026-10-16 | 2026-11-09 | 0 |  |  | 24 |  |  | Sameer Iyer |  |  | 2 | [8 empty] | 2026-10-16 | 2026-11-09
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | UAT - Task 214 | Completed | 2026-08-10 | 2026-08-22 | 1 |  |  | 12 | [5 empty] | 5 |  | 2026-08-09 | 2026-08-23 | 1d |  |  |  |  | 2026-08-10 | 2026-08-22
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Red | Build - Task 215 | Completed | 2026-03-23 | 2026-03-31 | 1 |  |  | 8 | [5 empty] | 0 |  | 2026-03-26 | 2026-03-28 | -3d |  |  |  |  | 2026-03-23 | 2026-03-31 | Red
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Green | Go-Live - Task 216 | Completed | 2026-10-13 | 2026-11-01 | 1 |  |  | 19 | [5 empty] | 0 | [8 empty] | 2026-10-13 | 2026-11-01 | Green
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | Testing - Task 217 | In Progress | 2026-02-08 | 2026-03-05 | 0.44 |  |  | 25 |  |  | Priya Menon |  |  | -1 |  | 2026-02-09 | 2026-03-01 | -4d |  |  |  |  | 2026-02-08 | 2026-03-05
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Build - Task 218 | Completed | 2026-03-11 | 2026-04-05 | 1 |  |  | 25 |  |  | Neha Kulkarni |  |  | 60 |  | 2026-03-09 | 2026-04-07 | 2d |  |  |  |  | 2026-03-11 | 2026-04-05
| S2P Implementation | 3 | Kavita Deshmukh | 3 | Testing |  | Green | Testing - Task 219 | Completed | 2026-06-08 | 2026-07-01 | 1 |  |  | 23 | [5 empty] | 0 |  | 2026-06-09 | 2026-07-01 | 0d |  | Supply Chain |  | Vendor Team | 2026-06-08 | 2026-07-01 | Green
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Green | Configuration - Task 220 | Not Started | 2026-07-09 | 2026-07-13 | 0 |  |  | 4 |  |  | Neha Kulkarni |  |  | -3 |  | 2026-07-12 | 2026-07-06 | -7d |  |  |  | Priya Menon | 2026-07-09 | 2026-07-13
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | UAT - Task 221 | In Progress | 2026-02-15 | 2026-03-03 | 0.4 |  |  | 16 | [5 empty] | 0 | [8 empty] | 2026-02-15 | 2026-03-03
| S2P Implementation | 1 | Kavita Deshmukh | 1 | Testing |  | Green | Testing - Task 222 | In Progress | 2026-05-24 | 2026-06-12 | 0.78 |  |  | 19 | [5 empty] | -3 | [7 empty] | Client IT | 2026-05-24 | 2026-06-12
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | Configuration - Task 223 | Completed | 2026-08-11 | 2026-08-15 | 1 |  |  | #UNPARSEABLE |  |  | Priya Menon |  |  | 5 | TRUE | 2026-08-06 | 2026-08-08 | -7d |  |  |  |  | 2026-08-11 | 2026-08-15
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Yellow | Hypercare - Task 224 | Completed | 2026-03-22 | 2026-04-09 | 1 |  |  | 18 |  |  | Neha Kulkarni |  |  | 12 |  | 2026-03-18 | 2026-04-04 | -5d | On track, no issues |  |  | Arjun Rao | 2026-03-22 | 2026-04-09
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Build - Task 225 | In Progress | 2026-03-12 | 2026-03-24 | 0.41 |  |  | 12 |  |  | Arjun Rao |  |  | 12 | [8 empty] | 2026-03-12 | 2026-03-24 | Green
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Build - Task 226 | Not Started | 2026-10-07 | 2026-10-19 | 0 |  |  | 12 | [5 empty] | 2 | [7 empty] | Neha Kulkarni | 2026-10-07 | 2026-10-19 | Red
| S2P Implementation | 3 | Kavita Deshmukh | 3 | Design |  | Green | Design - Task 227 | In Progress | 2026-06-20 | 2026-06-23 | 0.63 |  |  | 3 | [5 empty] | 8 | [8 empty] | 2026-06-20 | 2026-06-23
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | Testing - Task 228 | Not Started | 2026-06-06 | 2026-06-27 | 0 |  |  | 21 | [5 empty] | -3 |  | 2026-06-08 | 2026-06-26 | -1d |  |  |  |  | 2026-06-06 | 2026-06-27
| S2P Implementation | 1 | Kavita Deshmukh | 3 | Testing |  | Green | Testing - Task 229 | Not Started | 2026-10-12 | 2026-10-17 | 0 |  |  | 5 |  |  | Sameer Iyer |  |  | 35 | [8 empty] | 2026-10-12 | 2026-10-17
| S2P Implementation | 2 | Kavita Deshmukh | 3 |  |  | Yellow | UAT - Task 230 | Completed | 2026-09-01 | 2026-09-19 | 1 |  |  | 18 | [5 empty] | 12 |  | 2026-08-28 | 2026-09-21 | 2d |  |  |  | Sameer Iyer | 2026-09-01 | 2026-09-19 | Green
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Red | Build - Task 231 | Completed | 2026-07-05 | 2026-07-14 | 1 |  |  | 9 |  |  | Neha Kulkarni |  |  | -3 | [8 empty] | 2026-07-05 | 2026-07-14
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Green | Build - Task 232 | Not Started | 2026-03-08 | 2026-04-01 | 0 |  |  | 24 | [5 empty] | 20 | [7 empty] | Vendor Team | 2026-03-08 | 2026-04-01
| S2P Implementation | 2 | Kavita Deshmukh | 1 |  |  | Green | UAT - Task 233 | Not Started | 2026-06-16 | 2026-07-02 | 0 |  |  | 16 | [5 empty] | 12 | [7 empty] | Vendor Team | 2026-06-16 | 2026-07-02
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Go-Live - Task 234 | Completed | 2026-08-07 | 2026-08-22 | 1 |  |  | 15 | [5 empty] | 2 |  | 2026-08-07 | 2026-08-15 | -7d |  |  |  |  | 2026-08-07 | 2026-08-22 | Green
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Build - Task 235 | Not Started | 2026-08-12 | 2026-08-29 | 0 |  |  | 17 | [5 empty] | -3 |  |  |  |  | Delayed due to scope clarification with stakeholders |  |  |  | 2026-08-12 | 2026-08-29
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Green | UAT - Task 236 | Not Started | 2026-09-16 | 2026-10-11 | 0 |  |  | 25 | [5 empty] | 0 |  | 2026-09-12 | 2026-10-03 | -8d |  |  |  |  | 2026-09-16 | 2026-10-11 | Green
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Green | UAT - Task 237 | In Progress | 2026-09-01 | 2026-09-20 | 0.11 |  |  | 19 | [5 empty] | -3 | [8 empty] | 2026-09-01 | 2026-09-20 | Green
| S2P Implementation | 2 | Kavita Deshmukh | 3 | Testing |  | Green | Testing - Task 238 | Completed | 2026-06-07 | 2026-06-25 | 1 |  |  | 18 |  |  | Divya Shah |  |  | 8 |  | 2026-06-02 | 2026-06-27 | 2d |  |  |  |  | 2026-06-07 | 2026-06-25 | Yellow
| S2P Implementation | 2 | Kavita Deshmukh | 2 |  |  | Green | UAT - Task 239 | Completed | 2026-03-31 | 2026-04-18 | 1 |  |  | 18 | [5 empty] | 20 | [8 empty] | 2026-03-31 | 2026-04-18 | Yellow
| S2P Implementation | 2 | Kavita Deshmukh | 2 | Configuration |  | Green | Configuration - Task 240 | In Progress | 2026-09-11 | 2026-09-22 | 0.66 |  |  | 11 |  |  | Divya Shah |  |  | 8 |  | 2026-09-08 | 2026-09-25 | 3d |  |  |  |  | 2026-09-11 | 2026-09-22 | Red
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Configuration - Task 241 | Completed | 2026-04-21 | 2026-05-10 | 1 |  |  | 19 | [5 empty] | 60 | TRUE | 2026-04-22 | 2026-05-08 | -2d |  |  |  |  | 2026-04-21 | 2026-05-10
| S2P Implementation | 3 | Kavita Deshmukh | 3 |  |  | Red | Design - Task 242 | Completed | 2026-03-19 | 2026-04-03 | 1 |  |  | 15 |  |  | Sameer Iyer |  |  | -1 | [8 empty] | 2026-03-19 | 2026-04-03
| S2P Implementation | 3 | Kavita Deshmukh | 2 | Testing |  | Red | Testing - Task 243 | Completed | 2026-07-01 | 2026-07-05 | 1 |  |  | 4 |  |  | Divya Shah |  |  | 35 |  | 2026-06-30 | 2026-07-06 | 1d |  |  |  |  | 2026-07-01 | 2026-07-05
| S2P Implementation | 1 | Kavita Deshmukh | 3 | Hypercare |  | Green | Hypercare - Task 244 | Not Started | 2026-01-12 | 2026-01-16 | 0 | Yes |  | 4 |  |  | Arjun Rao |  |  | 8 | [7 empty] | Divya Shah | 2026-01-12 | 2026-01-16
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Green | UAT - Task 245 | Not Started | 2026-02-09 | 2026-03-04 | 0 |  |  | 23 | [5 empty] | -1 |  |  |  |  | Delayed due to scope clarification with stakeholders |  |  |  | 2026-02-09 | 2026-03-04 | Red
| S2P Implementation | 2 | Kavita Deshmukh | 1 | Design |  | Green | Design - Task 246 | Completed | 2026-04-19 | 2026-04-26 | 1 |  |  | 7 | [5 empty] | -3 |  | 2026-04-22 | 2026-04-18 | -8d | On track, no issues |  |  |  | 2026-04-19 | 2026-04-26 | Green
| S2P Implementation | 2 | Kavita Deshmukh | 3 | Build |  | Green | Build - Task 247 | Completed | 2026-02-17 | 2026-02-21 | 1 |  |  | 4 | [5 empty] | 35 | [8 empty] | 2026-02-17 | 2026-02-21
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Yellow | Design - Task 248 | Not Started | 2026-05-04 | 2026-05-09 | 0 |  |  | 5 |  |  | Sameer Iyer |  |  | 20 | [8 empty] | 2026-05-04 | 2026-05-09 | Green
| S2P Implementation | 3 | Kavita Deshmukh | 2 |  |  | Yellow | Build - Task 249 | Completed | 2026-08-24 | 2026-09-03 | 1 |  |  | #UNPARSEABLE | [5 empty] | 0 | [8 empty] | 2026-08-24 | 2026-09-03
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Green | Build - Task 250 | Not Started | 2026-10-06 | 2026-10-23 | 0 |  |  | 17 | [5 empty] | 0 |  | 2026-10-07 | 2026-10-17 | -6d |  |  |  |  | 2026-10-06 | 2026-10-23
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Red | Configuration - Task 251 | In Progress | 2026-04-28 | 2026-05-09 | 0.6 |  |  | 11 | [5 empty] | -1 |  | 2026-04-30 | 2026-05-10 | 1d |  |  |  | Client IT | 2026-04-28 | 2026-05-09
| S2P Implementation | 1 | Kavita Deshmukh | 2 |  |  | Green | Discovery - Task 252 | In Progress | 2026-05-12 | 2026-05-29 | 0.19 |  |  | 17 |  |  | Arjun Rao |  |  | 12 | [7 empty] | Divya Shah | 2026-05-12 | 2026-05-29
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Green | Hypercare - Task 253 | Not Started | 2026-09-03 | 2026-09-12 | 0 |  |  | 9 | [5 empty] | 8 | [8 empty] | 2026-09-03 | 2026-09-12
| S2P Implementation | 3 | Kavita Deshmukh | 1 |  |  | Yellow | Build - Task 254 | In Progress | 2026-05-09 | 2026-05-14 | 0.54 |  |  | 5 |  |  | Arjun Rao |  |  | 5 |  | 2026-05-04 | 2026-05-10 | -4d |  |  |  |  | 2026-05-09 | 2026-05-14 | Yellow
| S2P Implementation | 3 | Kavita Deshmukh | 3 | Discovery |  | Green | Discovery - Task 255 | In Progress | 2026-03-03 | 2026-03-20 | #UNPARSEABLE |  |  | 17 | [5 empty] | 0 |  | 2026-03-05 | 2026-03-15 | -5d |  |  |  |  | 2026-03-03 | 2026-03-20
| S2P Implementation | 1 | Kavita Deshmukh | 3 |  |  | Yellow | Go-Live - Task 256 | Not Started | 2026-09-06 | 2026-10-01 | 0 |  |  | 25 | [5 empty] | -1 | [7 empty] | Vendor Team | 2026-09-06 | 2026-10-01
| S2P Implementation | 3 | Kavita Deshmukh | 3 | UAT |  | Green | UAT - Task 257 | Completed | 2026-07-18 | 2026-08-04 | 1 |  |  | 17 | [5 empty] | 12 | [7 empty] | Priya Menon | 2026-07-18 | 2026-08-04
| S2P Implementation | 1 | Kavita Deshmukh | 1 |  |  | Green | Testing - Task 258 | In Progress | 2026-02-08 | 2026-02-13 | 0.44 |  |  | 5 | [5 empty] | 60 |  | 2026-02-04 | 2026-02-09 | -4d |  |  |  | Sameer Iyer | 2026-02-08 | 2026-02-13
| S2P Implementation | 1 | Kavita Deshmukh | 1 | Testing |  | Green | Testing - Task 259 | Completed | 2026-04-06 | 2026-04-17 | 1 |  |  | 11 | [5 empty] | 2 |  | 2026-04-07 | 2026-04-13 | -4d |  |  |  |  | 2026-04-06 | 2026-04-17 | Red

## Comments
Row 173 | Escalation raised regarding data migration accuracy in finance module. | Divya Shah | 06/26/26 2:25 PM
Row 169 | Escalation raised regarding data migration accuracy in finance module. | Divya Shah | 06/26/26 2:25 PM
Row 229 | Escalation raised regarding data migration accuracy in finance module. | Priya Menon | 06/26/26 2:25 PM
Row 69 | Resourcing gap on client IT side may impact UAT start date. | Priya Menon | 06/26/26 2:25 PM
Row 135 | Vendor integration testing pushed by a week due to sandbox access delay. | Arjun Rao | 06/26/26 2:25 PM
Row 149 | Resourcing gap on client IT side may impact UAT start date. | Neha Kulkarni | 06/26/26 2:25 PM
Row 182 | Great progress this sprint, ahead of the configuration milestones. | Arjun Rao | 06/26/26 2:25 PM

## Summary
Project Name
Project Manager | Kavita Deshmukh
Project Start Date | 2026-01-12
Project End Date | 2026-11-20
Not Started | 91
In Progress | 34
Completed | 134
On Hold | 1
At Risk | Medium
Project Stage | Configuration and Build phase
% Complete | 0.52
Schedule Health | Yellow
Today's Date | 2026-07-02
Target Start Date
Target End Date
Schedule Delta
Duration | 312
Target Dates Variance
Schedule Variance
Project Status | In Progress